Next steps as agreed in the first co-ordination meeting (Barcelona, 15-17 November 2012) List of the attachement
1. AIPD will send this list to partners by the 20th of November 2012 (AIPD)
2. Discuss and send back the contract with aipd (FCSD, HUDF, IFI)
3. Report of the first coordination meeting , 30 November 2012(AIPD)
4. Review the project and the budget in order to clarify everything(FCSD, HUDF, IFI)
5. Receive the tools (as changed during the coordination meeting) for FG and Exchange e mails with the expert, Clio Marco Veronesi. (FCSD, HUDF, IFI)
6. Starting selection of participants in the FGs (All)
7. Finding premises for the FGs (HUDF)
8. First financial report, by the end of January 2013 (to Maria Giulia Senni) (FCSD, HUDF,IFI)
9. Prepare the web site and the dissemination plan. Katalin will send a `proposal Drupal+ sharing of documents (Google drive ). Web site must be published by 18 January 2013 (HUDF)
10. Facebook page must be ready by 18 January 2013 (HUDF)
11. Preparation of the next meeting (programme, hotel, venue, visit to the Foundation) (HUDF)
12. Evaluation plan by the 29th of March 2013 (AIPD)
13. Dissemination plan by the 30th of November (AIPD will send Katalin the translation of the relevant wp contained in the Project) (AIPD + HUDF)
14. Send AIPD an estimate of the expenses for graphic and printing. (FCSD, HUDF, IFI)
 

 

List of the attachement
1. Presentacciòn FCSD angles 
2. PPT AIPD
3. PPT Presentacciòn IFI
4. AIPD PPTDAHUGK
5. pre progetto team building next steps_RIV
6. Dissemination and website2
7. FINANCIAL INFORMATION
8. PPT - WP 3 Focus Groups IFI
